## Data Validation (hidden)
Color Code | Status | App | Business Unit
Green | Open | cA | Revenue Management
Orange | Delivered | RC | International
Yellow | Closed | Both | Choice Privilege
Security
Other

## Defect Statistics Dashboard (hidden)
| Pre 2016 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
New Defect Opened (with known open date) | 22 | 5 | 5 | 8 | 14 | 6 | 3 | 2 | 4 | 2 | 5
Total Defects for YTD | 24 | 29 | 34 | 42 | 56 | 62 | 65 | 67 | 71 | 73 | 78
Total Open Defects | 15 | 5 | 4 | 1 | 9 | 3 | 3 | 2 | 4 | 1 | 5
Total Open Defects YTD | 15 | 20 | 24 | 25 | 34 | 37 | 40 | 42 | 46 | 47 | 52

## Age Data (Hidden) (hidden)
HOS# | Color Code(To be Hide) | Date Opened | Case/SR | Closed? | Delivered in | Delivered/Closed Date | Age | App | AgePre2016 | AgeJan2016 | AgeFeb2016 | AgeMar2016 | AgeApr2016 | AgeMay2016 | AgeJun2016 | AgeJuly2016 | AgeAug2016 | AgeSept2016 | AgeOct2016 | AgeNov2016 | AgeDec2016 | AgeJan2017 | AgeFeb2017
HOS-9314 |  | 2016-02-23 |  | Closed | N/A, CIS needs to fix the data being fed into cA | 2016-08-22 | 181 | cA | N/A | N/A | 7 | 38 | 68 | 99 | 129 | 160 | 181 | N/A | N/A | N/A | N/A | N/A | N/A
HOS-8665 |  | 2016-01-20 |  | Open |  |  | 401 |  | N/A | 12 | 41 | 72 | 102 | 133 | 163 | 194 | 225 | 255 | 286 | 316 | 347 | 378 | 401
HOS-10603 |  | 2016-03-29 |  | Delivered | RC 5.7.3 | 2016-07-28 | 121 | RC | N/A | N/A | N/A | 3 | 33 | 64 | 94 | 121 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HOS-9263 |  | 2016-03-09 |  | Delivered | RC 5.7.3 | 2016-07-28 | 141 | RC | N/A | N/A | N/A | 23 | 53 | 84 | 114 | 141 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HOS-575 |  | 2015-11-10 |  | Delivered | RC 5.9 | 2016-11-10 | 366 | RC | 52 | 83 | 112 | 143 | 173 | 204 | 234 | 265 | 296 | 326 | 357 | 366 | N/A | N/A | N/A
HOS-10302 |  | 2016-03-18 |  | Closed |  | 2016-11-09 | 236 | Both | N/A | N/A | N/A | 14 | 44 | 75 | 105 | 136 | 167 | 197 | 228 | 236 | N/A | N/A | N/A
HOS-4766 |  | 2016-03-31 |  | Delivered | RC 5.9 | 2016-11-10 | 224 | RC | N/A | N/A | N/A | 1 | 31 | 62 | 92 | 123 | 154 | 184 | 215 | 224 | N/A | N/A | N/A
HOS-11023 | Green | 2016-04-19 |  | Open |  |  | 311 | RC | N/A | N/A | N/A | N/A | 12 | 43 | 73 | 104 | 135 | 165 | 196 | 226 | 257 | 288 | 311 | 2016-01-01 | 42370
HOS-6130 |  | 2015-10-15 |  | Delivered | RC 5.9 | 2016-11-10 | 392 | RC | 78 | 109 | 138 | 169 | 199 | 230 | 260 | 291 | 322 | 352 | 383 | 392 | N/A | N/A | N/A | 2016-02-01 | 42401
HOS-8331 |  | 2016-02-16 |  | Open |  |  | 374 |  | N/A | N/A | 14 | 45 | 75 | 106 | 136 | 167 | 198 | 228 | 259 | 289 | 320 | 351 | 374 | 2016-03-01 | 42430
HOS-9900 |  | 2016-03-14 |  | Delivered | RC 5.13 | 2017-02-02 | 325 | RC | N/A | N/A | N/A | 18 | 48 | 79 | 109 | 140 | 171 | 201 | 232 | 262 | 293 | 324 | 325 | 2016-04-01 | 42461
HOS-7603 |  | 2015-12-15 |  | Closed | N/A, ST could not replicate as of June 2016 at least, and Edge did not have time to validate nor reported it as an ongoing issue | 2016-06-22 | 190 | RC | 17 | 48 | 77 | 108 | 138 | 169 | 190 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-05-01 | 42491
HOS-7604 |  | 2015-12-15 |  | Closed | N/A, ST could not replicate as of June 2016 at least, and Edge did not have time to validate nor reported it as an ongoing issue | 2016-06-22 | 190 | RC | 17 | 48 | 77 | 108 | 138 | 169 | 190 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-06-01 | 42522
HOS-9633 |  | 2015-10-01 |  | Delivered | RC 5.13 | 2017-02-02 | 490 |  | 92 | 123 | 152 | 183 | 213 | 244 | 274 | 305 | 336 | 366 | 397 | 427 | 458 | 489 | 490 | 2016-07-01 | 42552
HOS-10525 | Orange | 2016-03-20 |  | Open |  |  | 341 | cA | N/A | N/A | N/A | 12 | 42 | 73 | 103 | 134 | 165 | 195 | 226 | 256 | 287 | 318 | 341 | 2016-08-01 | 42583
HOS-10512 |  | 2016-02-16 |  | Open |  |  | 374 |  | N/A | N/A | 14 | 45 | 75 | 106 | 136 | 167 | 198 | 228 | 259 | 289 | 320 | 351 | 374 | 2016-09-01 | 42614
HOS-7973 | Orange | 2016-01-05 |  | Open |  |  | 416 | cA | N/A | 27 | 56 | 87 | 117 | 148 | 178 | 209 | 240 | 270 | 301 | 331 | 362 | 393 | 416 | 2016-10-01 | 42644
HOS-11129 |  | 2016-04-18 |  | Delivered | RC 5.7.3 | 2016-07-28 | 101 | RC | N/A | N/A | N/A | N/A | 13 | 44 | 74 | 101 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-11-01 | 42675
HOS-11256 |  | 2016-04-20 |  | Delivered | RC 5.9 | 2016-11-10 | 204 | RC | N/A | N/A | N/A | N/A | 11 | 42 | 72 | 103 | 134 | 164 | 195 | 204 | N/A | N/A | N/A | 2016-12-01 | 42705
HOS-11429 |  | 2016-04-21 |  | Delivered | cA 8.5 | 2016-10-27 | 189 | cA | N/A | N/A | N/A | N/A | 10 | 41 | 71 | 102 | 133 | 163 | 189 | N/A | N/A | N/A | N/A | 2017-01-01 | 42736
HOS-11435 |  | 2016-04-22 |  | Delivered | RC 5.10 | 2016-11-28 | 220 | RC | N/A | N/A | N/A | N/A | 9 | 40 | 70 | 101 | 132 | 162 | 193 | 220 | N/A | N/A | N/A | 2017-02-01 | 42767
HOS-11258 |  | 2016-04-13 |  | Open |  |  | 317 | RC | N/A | N/A | N/A | N/A | 18 | 49 | 79 | 110 | 141 | 171 | 202 | 232 | 263 | 294 | 317 | 2017-03-01 | 42795
HOS-8755 |  | 2016-03-18 |  | Delivered | cA 8.5 | 2016-10-27 | 223 | cA | N/A | N/A | N/A | 14 | 44 | 75 | 105 | 136 | 167 | 197 | 223 | N/A | N/A | N/A | N/A | 2017-04-01 | 42826
HOS-11774 | Green | 2016-04-22 |  | Open |  |  | 308 | cA | N/A | N/A | N/A | N/A | 9 | 40 | 70 | 101 | 132 | 162 | 193 | 223 | 254 | 285 | 308 | 2017-05-01 | 42856
HOS-11381 |  | 2016-04-18 |  | Delivered | cA 8.2.0.14 | 2016-08-25 | 129 | cA | N/A | N/A | N/A | N/A | 13 | 44 | 74 | 105 | 129 | N/A | N/A | N/A | N/A | N/A | N/A | 2017-06-01 | 42887
HOS-11610 |  | 2016-05-05 |  | Open |  |  | 295 |  | N/A | N/A | N/A | N/A | N/A | 27 | 57 | 88 | 119 | 149 | 180 | 210 | 241 | 272 | 295 | 2017-07-01 | 42917
HOS-9679 |  | 2016-03-10 |  | Delivered | RC 5.9 | 2016-11-10 | 245 | RC | N/A | N/A | N/A | 22 | 52 | 83 | 113 | 144 | 175 | 205 | 236 | 245 | N/A | N/A | N/A | 2017-08-01 | 42948
HOS-11254 | Orange | 2016-04-20 |  | Open |  |  | 310 |  | N/A | N/A | N/A | N/A | 11 | 42 | 72 | 103 | 134 | 164 | 195 | 225 | 256 | 287 | 310 | 2017-09-01 | 42979
HOS-8749 |  | 2016-05-10 |  | Delivered | cA 8.2 | 2016-07-20 | 71 | cA | N/A | N/A | N/A | N/A | N/A | 22 | 52 | 71 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2017-10-01 | 43009
HOS-10959 |  | 2016-04-19 |  | Open |  |  | 311 |  | N/A | N/A | N/A | N/A | 12 | 43 | 73 | 104 | 135 | 165 | 196 | 226 | 257 | 288 | 311 | 2017-11-01 | 43040
HOS-10922 |  | 2016-04-05 |  | Open |  |  | 325 | RC | N/A | N/A | N/A | N/A | 26 | 57 | 87 | 118 | 149 | 179 | 210 | 240 | 271 | 302 | 325 | 2017-12-01 | 43070
HOS-11440 | Green | 2016-04-28 |  | Open |  |  | 302 | cA | N/A | N/A | N/A | N/A | 3 | 34 | 64 | 95 | 126 | 156 | 187 | 217 | 248 | 279 | 302
HOS-11952 | Green | 2016-05-18 |  | Open |  |  | 282 | cA | N/A | N/A | N/A | N/A | N/A | 14 | 44 | 75 | 106 | 136 | 167 | 197 | 228 | 259 | 282
HOS-2428 |  | 2014-09-19 |  | Delivered | cA 8.5 | 2016-10-27 | 769 | cA | 469 | 500 | 529 | 560 | 590 | 621 | 651 | 682 | 713 | 743 | 769 | N/A | N/A | N/A | N/A
HOS-2317 | Green | 2014-09-19 |  | Open |  |  | 889 |  | 469 | 500 | 529 | 560 | 590 | 621 | 651 | 682 | 713 | 743 | 774 | 804 | 835 | 866 | 889
HOS-2281 | Green | 2014-09-19 |  | Open |  |  | 889 |  | 469 | 500 | 529 | 560 | 590 | 621 | 651 | 682 | 713 | 743 | 774 | 804 | 835 | 866 | 889
HOS-1222 |  | 2014-09-19 |  | Closed | Cannot be reproduced, SkyTouch Confirmed that the title is translated | 2016-11-22 | 795 |  | 469 | 500 | 529 | 560 | 590 | 621 | 651 | 682 | 713 | 743 | 774 | 795 | N/A | N/A | N/A
HOS-1274 |  | 2014-10-27 |  | Closed | Working as designed, user can update the information in the extended guest data section | 2016-12-07 | 772 |  | 431 | 462 | 491 | 522 | 552 | 583 | 613 | 644 | 675 | 705 | 736 | 766 | 772 | N/A | N/A
HOS-12627 |  | 2016-05-31 |  | Delivered | RC 5.7.3 | 2016-07-28 | 58 | RC | N/A | N/A | N/A | N/A | N/A | 1 | 31 | 58 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HOS-12500 |  | 2016-05-25 |  | Delivered | RC 5.7.3 | 2016-07-28 | 64 | RC | N/A | N/A | N/A | N/A | N/A | 7 | 37 | 64 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HOS-14978 | Green | 2016-08-12 | 34688 | Open |  |  | 196 | RC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 20 | 50 | 81 | 111 | 142 | 173 | 196
HOS-15890 |  | 2016-09-09 | 36908 | Delivered | RC 5.11 | 2016-12-15 | 97 | RC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 22 | 53 | 83 | 97 | N/A | N/A
HOS-2395 |  | 2015-06-25 |  | Open |  |  | 610 |  | 190 | 221 | 250 | 281 | 311 | 342 | 372 | 403 | 434 | 464 | 495 | 525 | 556 | 587 | 610
HOS-14118 | Green | 2016-08-17 |  | Open |  |  | 191 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 15 | 45 | 76 | 106 | 137 | 168 | 191
HOS-10579 |  | 2016-06-08 |  | Open |  |  | 261 |  | N/A | N/A | N/A | N/A | N/A | N/A | 23 | 54 | 85 | 115 | 146 | 176 | 207 | 238 | 261
HOS-2038 | Green | 2015-07-09 |  | Open |  |  | 596 |  | 176 | 207 | 236 | 267 | 297 | 328 | 358 | 389 | 420 | 450 | 481 | 511 | 542 | 573 | 596
HOS-8837 |  | 2016-02-04 |  | Open |  |  | 386 |  | N/A | N/A | 26 | 57 | 87 | 118 | 148 | 179 | 210 | 240 | 271 | 301 | 332 | 363 | 386
HOS-15425 | Green | 2016-09-22 |  | Open |  |  | 155 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 9 | 40 | 70 | 101 | 132 | 155
HOS-13227 | Green | 2016-07-10 |  | Open |  |  | 229 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 22 | 53 | 83 | 114 | 144 | 175 | 206 | 229
HOS-13237 |  | 2016-07-11 |  | Open |  |  | 228 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 21 | 52 | 82 | 113 | 143 | 174 | 205 | 228
HOS-2322 | Green | 2014-09-19 |  | Open |  |  | 889 |  | 469 | 500 | 529 | 560 | 590 | 621 | 651 | 682 | 713 | 743 | 774 | 804 | 835 | 866 | 889
HOS-13805 |  | 2016-08-03 |  | Open |  |  | 205 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 29 | 59 | 90 | 120 | 151 | 182 | 205
HOS-9199 |  | 2016-02-25 |  | Open |  |  | 365 |  | N/A | N/A | 5 | 36 | 66 | 97 | 127 | 158 | 189 | 219 | 250 | 280 | 311 | 342 | 365
HOS-12973 |  | 2016-01-08 |  | Open |  |  | 413 | cA | N/A | 24 | 53 | 84 | 114 | 145 | 175 | 206 | 237 | 267 | 298 | 328 | 359 | 390 | 413
HOS-8041 |  | 2016-01-07 |  | Open |  |  | 414 | cA | N/A | 25 | 54 | 85 | 115 | 146 | 176 | 207 | 238 | 268 | 299 | 329 | 360 | 391 | 414
HOS-2445 | Green | 2015-12-18 |  | Open |  |  | 434 | cA | 14 | 45 | 74 | 105 | 135 | 166 | 196 | 227 | 258 | 288 | 319 | 349 | 380 | 411 | 434
HOS-657 | Green | 2015-09-22 |  | Open |  |  | 521 | cA | 101 | 132 | 161 | 192 | 222 | 253 | 283 | 314 | 345 | 375 | 406 | 436 | 467 | 498 | 521
HOS-1988 | Green | 2015-09-18 |  | Open |  |  | 525 | cA | 105 | 136 | 165 | 196 | 226 | 257 | 287 | 318 | 349 | 379 | 410 | 440 | 471 | 502 | 525
HOS-1843 |  | 2015-05-21 |  | Closed | SkyTouch verified it was working, could not reproducce it, since package feature was not rolled out to properties, no report from property | 2016-12-07 | 566 | RC | 225 | 256 | 285 | 316 | 346 | 377 | 407 | 438 | 469 | 499 | 530 | 560 | 566 | N/A | N/A
HOS-13110 | Orange | 2016-06-30 |  | Open |  |  | 239 | cA | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 32 | 63 | 93 | 124 | 154 | 185 | 216 | 239
HOS-11599 | Orange | 2016-05-04 |  | Open |  |  | 296 | RC | N/A | N/A | N/A | N/A | N/A | 28 | 58 | 89 | 120 | 150 | 181 | 211 | 242 | 273 | 296
HOS-10695 |  |  |  | Delivered | CH.COM fix on Oct.11 | 2016-10-11 | N/A | cA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HOS-14491 |  |  |  | Delivered | CR20666 and CR20867 | 2016-09-15 | N/A | RC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HOS-12665 |  | 2016-06-10 |  | Open |  |  | 259 | cA | N/A | N/A | N/A | N/A | N/A | N/A | 21 | 52 | 83 | 113 | 144 | 174 | 205 | 236 | 259
HOS-16405 | Green | 2016-11-03 |  | Open |  |  | 113 | cA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 28 | 59 | 90 | 113
HOS-16469 |  | 2016-08-24 |  | Open |  |  | 184 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 8 | 38 | 69 | 99 | 130 | 161 | 184
HOS-16518 | Green | 2016-11-09 |  | Open |  |  | 107 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 22 | 53 | 84 | 107
HOS-1398 | Green | 2015-07-12 |  | Open |  |  | 593 |  | 173 | 204 | 233 | 264 | 294 | 325 | 355 | 386 | 417 | 447 | 478 | 508 | 539 | 570 | 593
HOS-14677 | Green | 2016-11-16 |  | Open |  |  | 100 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 15 | 46 | 77 | 100
HOS-8154 |  | 2016-01-11 |  | Open |  |  | 410 |  | N/A | 21 | 50 | 81 | 111 | 142 | 172 | 203 | 234 | 264 | 295 | 325 | 356 | 387 | 410
HOS-16790 |  | 2016-11-21 |  | Open |  |  | 95 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10 | 41 | 72 | 95
HOS-17019 |  | 2016-10-27 |  | Open |  |  | 120 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 5 | 35 | 66 | 97 | 120
HOS-8744 | Orange | 2014-09-19 |  | Open |  |  | 889 |  | 469 | 500 | 529 | 560 | 590 | 621 | 651 | 682 | 713 | 743 | 774 | 804 | 835 | 866 | 889
HOS-5835 | Green | 2015-10-19 |  | Open |  |  | 494 |  | 74 | 105 | 134 | 165 | 195 | 226 | 256 | 287 | 318 | 348 | 379 | 409 | 440 | 471 | 494
HOS-17252 | Green | 2016-12-20 |  | Open |  |  | 66 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 12 | 43 | 66
HOS-17317 |  | 2016-12-23 |  | Open |  |  | 63 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 9 | 40 | 63
HOS-17287 |  | 2016-12-19 |  | Open |  |  | 67 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 13 | 44 | 67
HOS-10697 |  | 2016-10-13 |  | Open |  |  | 134 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 19 | 49 | 80 | 111 | 134
HOS-15934 | Green | 2016-10-11 |  | Open |  |  | 136 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 21 | 51 | 82 | 113 | 136
HOS-17271 | Green | 2016-12-02 |  | Open |  |  | 84 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30 | 61 | 84
HOS-17331 |  | 2016-12-16 |  | Open |  |  | 70 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 16 | 47 | 70
HOS-17330 |  | 2016-10-18 |  | Open |  |  | 129 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 14 | 44 | 75 | 106 | 129
HOS-17638 |  | 2016-12-02 | 44212 | Closed | Tracked as enhancement HOS-14612 | 2017-01-18 | 47 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30 | 47 | N/A
HOS-17061 |  | 2017-01-07 |  | Closed | Related to HOS-17252 | 2017-01-17 | 10 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10 | N/A
HOS-16098 | Orange | 2016-10-01 |  | Open |  |  | 146 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 31 | 61 | 92 | 123 | 146
HOS-17692 |  | 2016-12-13 | 44970 | Open |  |  | 73 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 19 | 50 | 73
HOS-2518 |  | 2014-09-19 |  | Open |  |  | 889 |  | 469 | 500 | 529 | 560 | 590 | 621 | 651 | 682 | 713 | 743 | 774 | 804 | 835 | 866 | 889
HOS-2232 |  | 2014-09-19 |  | Open |  |  | 889 |  | 469 | 500 | 529 | 560 | 590 | 621 | 651 | 682 | 713 | 743 | 774 | 804 | 835 | 866 | 889
HOS-11362 |  | 2016-04-26 |  | Open |  |  | 304 |  | N/A | N/A | N/A | N/A | 5 | 36 | 66 | 97 | 128 | 158 | 189 | 219 | 250 | 281 | 304
HOS-2513 |  | 2014-09-19 |  | Open |  |  | 889 |  | 469 | 500 | 529 | 560 | 590 | 621 | 651 | 682 | 713 | 743 | 774 | 804 | 835 | 866 | 889
HOS-17778 |  | 2016-12-27 | 46137 | Open |  |  | 59 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 5 | 36 | 59
HOS-17986 |  | 2016-12-21 | 45758 | Open |  |  | 65 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 11 | 42 | 65
HOS-18046 |  | 2017-02-07 | 49764 | Open |  |  | 17 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 17
HOS-1432 |  | 2015-02-26 |  | Open |  |  | 729 |  | 309 | 340 | 369 | 400 | 430 | 461 | 491 | 522 | 553 | 583 | 614 | 644 | 675 | 706 | 729
HOS-11346 |  | 2016-04-25 |  | Open |  |  | 305 |  | N/A | N/A | N/A | N/A | 6 | 37 | 67 | 98 | 129 | 159 | 190 | 220 | 251 | 282 | 305
HOS-18066 |  | 2017-01-10 | 47291 | Open |  |  | 45 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 22 | 45
Formulas:
Age = IF(OR(Age[[#This Row],[Closed?]]="Delivered", Age[[#This Row],[Closed?]]="Closed"), Age[[#This Row],[Delivered/Closed Date]]-Age[[#This Row],[Date Opened]], TODAY() - VLOOKUP([HOS#],'Age Data (Hidden)'!$A:$C,3,FALSE))
AgeFeb2017 = IF([Date Opened]<42795,IF([Delivered/Closed Date]<>"", IF([Delivered/Closed Date]<42767,"N/A", IF([Delivered/Closed Date] <42795,[Delivered/Closed Date]-[Date Opened],42795-[Date Opened])),TODAY()-[Date Opened]), "N/A")

## Dashboard
Defect Prioritization Weekly Status Update | [5 empty] | Average Age of Open Defects
Hotel Technology | [5 empty] | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-16 | 2017-01-01 | 2017-02-17
2017-02-24 | [5 empty] | 245.7931 | 236.3235 | 218.9524 | 189.5357 | 200.7903 | 220.5538 | 244.9231 | 273.7778 | 298.3968 | 306.2794 | 312.058 | 297.4143 | 311.2899 | 337.2941
In flight Fixes
| Total | cA Specific | Rate Center Specific | Both
Currently being worked on by SkyTouch | 23 | 7 | 2 | 0
Defects assigned to upcoming releases | 7 | 3 | 1 | 0
Prioritized Defect Breakdown
Total Prioritized Defects | 96 | 44 | 44 | 0 | Total Precentage%
Prioritized Open Defects | 66 | 37 | 27 | 0 | 68.75%
Delivered Prioritized Defects YTD | 21 | 6 | 14 | 0 | 21.88%
Closed Defect | 9 | 1 | 3 | 0 | 9.375%
Defects yet to be Prioritized | 0 | 0 | 0 | 0
Defects without known Date | 2
Prioritized Defect Age
Defects Opened 120 Days Or Longer | 48
Average Age of Open Defects (Days) | 329.4032
Average Age of Delivered Defects (Days) | 233.1053
Prioritized Open Defect Impacting Business Unit
Choice Privilege | 2
International | 14
Revenue Management | 25

## Open Defects
SkyTouch Defect List - Priority Items based on Choice awareness (not all defects listed)
Yellow items may need to be re-prioritized as they are new with significant impact per BO (typically near bottom of list)
Green items are currently being worked on by SkyTouch (in development or dev-complete and pending release planning)
Orange items are about to go into a release
# | ST Jira HOS# | App | Problem | Impact - Qualitative | Work around? | Recaps? | Number of properties | GRR Impact | Upscale Impact | Guest Satisfaction Impact | Program/Function Dependency | Repeating Problem | Choice Prioritization Rank | Age (days) | Status | Impacting Business Unit | Initiative Impacted | BO
| HOS-10525 | cA | The Future Reservations report does not display IATA number info | Cannot see IATA number for future reservations | No | N | [7 empty] | 341 | cA 8.8 | Other | Upscale | Abhijit Patel
| HOS-11599 | cA | Shift4 discrepency - no charge on Shift4, payment posted in PM |  | Yes | [8 empty] | 296 | cA 8.8 | Revenue Management
| HOS-7973 | cA | Tax Invoice - Internal Error when Generating Tax Invoice Guest/Group/House Accounts Beginning with Payment Adjustment | potential legal requirement | No | N | [7 empty] | 416 | cA 8.8 | International | International
| HOS-13110 | cA | Free Continental Breakfast Campaign in AU region not visible in cA, although it is in RC | Unsure if this means cA will reject all bookings or just block walkins | Yes | N | [7 empty] | 239 | cA 8.8 | International | International | Dan Davis
| HOS-8744 | cA | Cannot Select Multiple Postings and Move to Another Folio View | The issue is on a Guest Folio, the user is unable to select multiple postings so they can be moved to another folio view. | Yes |  | 100+ | Low | Yes | Low | No | No | Low | 889 | cA 8.8 | Other | Daily Ops | Kevin Hou
| HOS-11254 | cA | Issue printing house account receipts, unable to print house account folio | Started with 8.1, intermittent, does not affect every printing | No | N | [7 empty] | 310 | cA 8.8 | Other | Daily Ops | Rob Allen
| HOS-16098 | cA | Credit Card Types Incorrectly Getting Assigned to Credit Cards | [9 empty] | Very Low | 146 | cA 8.8
| HOS-5835 | cA | Credit Card Bin Range does not match actual card type | Guest would have to change another card or method of payment | No |  | 100+ | Low | Yes | High | No | No | High | 494 | In Dev | International | Daily Ops | David Beers
| HOS-11774 | cA | Guest Folio - Taxes Displaying in English where French Language Preference Selected, pre-condition: trans code modifiction flag and enabled, tax description has been modified | Can result in fines to Canadian properties for not having all items in French | No | N | [7 empty] | 308 | Release Planning | International | International | David Beers
| HOS-11440 | cA | Offline Emergency Reports - Folios are Not Included | Emergency reports are incomplete when generated | Yes | N | [7 empty] | 302 | On-Hold | Other | Daily Ops | David Beers
| HOS-11952 | cA | Offline Emergency Reports Not Generating In House List for All Properties | Emergency reports are incomplete when generated | Yes | N | [7 empty] | 282 | On-Hold | Other | Daily Ops | David Beers
| HOS-11023 | RC | Bar Conversion failure on Step 8: Send final recap, gets an error | Blocks conversions | No | N | [7 empty] | 311 | In Dev | Revenue Management | Conversions | Becky Snediker
| HOS-14978 | RC | When a property makes modifications to an Event the changes are not accurately being recorded in the change history tables of the database. | causes confusion when trying to troubleshoot possible issues involving changes | No | N | [7 empty] | 196 | Release Planning | Other | Daily Ops | Abhijit Patel
| HOS-2281 | cA | For International Properties - Print options - Folio reports are not translating as per the guest preferred language. Defaulting to the property langauge seting. | Can result in fines to any primary non-English property | No | N | [7 empty] | 889 | In Dev | International | International | David Beers
| HOS-16518 | cA | No central pickup URL displayed in UI when checking "Sell in CRS" for local created group | Prevent locally-created groups from being marked ‘Sell in CRS’ from receiving their booking URLs, this is the main thing holding us back from letting other properties use this feature | No |  | 100+ | High | Yes | Medium | Yes | No | Critical | 107 | On-Hold | Revenue Management | Group | Kevin Hou
| HOS-2038 | cA | Rates Center Packages (cA) - End Date Displayed in cA Does Not Match with RC | cA's end date fails to match up so it can be sold after the fact (as long as rates are present for those dates) | No | N | 100+ | Medium | Yes | High | No | No | High | 596 | Release Planning | Revenue Management | Packages | Kevin Hou
| HOS-14118 | cA | Housekeeping Check-Off Report - Departing Guests with Clean Room Displays Stay Over | Create confusion around room status, sometime the housekeeper goes into that room but the room is actually occupied | Yes | N | 100+ | Low | Yes | High | No | No | Low | 191 | Release Planning | International | International | Rob Allen
| HOS-2322 | cA | Day Use Room can be assigned to same room number as a guest already booked in that room for 2 nights | Last check-in I have a note that you were getting details on this, but you were able to confirm that this defect does not actually let you check someone into the room despite it not displaying the occupancy correctly. | No | N | 100+ | Low | Yes | High | No | No | High | 889 | In Dev | Other | Daily Ops | Abhijit Patel
| HOS-13227 | RC | RC Rate Plan Recaps and Property Recaps do not recap the same days, and some days are missed on property recaps that rate plan recaps correctly send (possibly vice-versa as well) | Requires even more recaps to get desired dates to recap | No | Y | 100+ | High | Yes | Low | No | No | High | 229 | On-Hold | Revenue Management | Recaps | Becky Snediker
| HOS-657 | cA | Group Folio - Internal Error when Viewing Credit Card Transaction Details | Cannot view payment transaction details (specifically for viewing individual transaction details on an in-house group folio) | No | N | 100+ | Low | Yes | Medium | No | No | Medium | 521 | Selected for Development | Other | Daily Ops | Kevin Hou
| HOS-16405 | cA | Guest Search within a reservation returns "guestProfileLookup_Form was not found" when toggling between "Search Guest By":" option | Unable to search CP members by name or phone number | Yes |  | 100+ | Low | Yes | High | No | No | Low | 113 | In Dev | Choice Privilege | Choice Privilege | Rob Allen
| HOS-14677 | cA | if a user selects Business Address as Primary, no business name displays on customer facing forms (tax invoice, credit notes, folio, etc.) | if a user selects Business Address as Primary, no address displays on customer facing forms (tax invoice, credit notes, folio, etc.) | No |  | 100+ | Low | No | High | No | No | Medium | 100 | In Dev |  | International | Anthony Stanley
| HOS-1988 | cA | Unable to book room package in cA only after inactivating a room type | Affects packages if a cA removes a room type from their property, impacts cA's ability to book for that package | Yes | N | 100+ | Medium | Yes | Low | No | No | Low | 525 | In Dev | Revenue Management | Packages | Kevin Hou
| HOS-2317 | cA | Report - French/German: Express checkout Report displays in English locale instead of desired locale (DE14115) | Can result in fines to any primary non-English property | No | N | [7 empty] | 889 | Selected for Development | International | International | David Beers
| HOS-17252 | RC | Allow Event Rates By Day not sending rate type in UpdateRate message | This causes the downstream systems to fail the message and not update their rates. | No |  | 100+ | Medium | Yes | Low | Yes | No | High | 66 | In Dev
| HOS-17271 | cA | Packages with Single Line Item Per Night printing multiple lines instead of just one | when a property creates a package and configures the charges to be bundled into a single line item per night, the resulting printout is displaying multiple lines for the charges instead of just a single line | No |  | 100+ | Low | No | High | No | No | Medium | 84 | In Dev | International | Packages | David Beers
| HOS-15934 | cA | packages getting assigned as travel agent commissionable when there is no UI to remove the flag | Travel agent receive commision when the rate plan should be non-commisionable | Yes |  | 100+ | Medium | Yes | Medium | No | Yes | Medium | 136 | In Dev | Other | Packages | Kevin Hou
| HOS-1398 | cA | House Folio Print out is not in the same order as how it shows in House Folio view | House Folio Print out is not in the same order as how it shows in House Folio view | No |  | 10-100 | Low | No | High | No | No | Low | 593 | Selected for Development | International | Daily Ops | Rob Allen
| HOS-2445 | cA | Email Group Folio from Invoice sends the folio with no postings. (DE8838) | Cannot directly email folio for group | Yes | N | 100+ | Low | Yes | High | No | No | Low | 434 | In Dev | Other | Daily Ops | Kevin Hou
| HOS-17287 | cA | Package reservation PTKTSL does not show up on the reservation activity report | cannot prepare the package amentity for guest arraival | Yes |  | 100+ | Medium | Yes | High | No | No | Low | 67 | In Dev | Revenue Management | Packages | Anne Gregory
1 | HOS-10579 | RC | From case 00036697: When the SmartRates API sends over an override request there are times that it takes an errorCode 13 message which reads: "Some error occurred during message". When this occurs the BAR Calendar in RC is displaying N/A for all Room Type Buckets. | BAR calendar shows rate as N/A after the SmartRate override. Repeating time is unknow,this is a HIGH priority for CHOC | No | N | 100+ | High | Yes | Low | Yes | No | Critical | 261 | Backlog | Revenue Management | Smart Rates | Kitti Tong
2 | HOS-17331 | RC | APR Child Rate Plans not calculating correct rate when rate bucket transfer set up | When a rate bucket transfer is added to a parent APR rate plan the relevant child APR rate plans are not updating with the correct rate, causing rate parity. | No |  | 10-100 | High | Yes | Low | No | No | Medium | 70 | Backlog | Revenue Management | Rate Parity | Kelly Money
3 | HOS-17692 | RC | If a property has an event scheduled on the BAR Calendar and they accept a SMART Rates override for a day that covers the event, the Event label is no longer displayed. (This is a cosmetic issue only) | Create confusion for users and they assume the event is gone in RC | No |  | 100+ | Low | Yes | Low | No | No | Medium | 73 | Backlog | Revenue Management | Smart Rates | Elizabeth Duke
4 | HOS-14662 | cA | $ sign is being printed instead of the correct currency sign and the word VAT is being replaced with GST | May result fine for international proeprties | No |  | 100+ | Low | No | High | No | No | Medium | #N/A | Backlog | International | International | David Beers
5 | HOS-16469 | RC | BAR Conversion failing during Step 1 for properties under Belgium and Poland, rate plans in Corporate RC are not configured with “Channels” at the country level for Belgium | Remove the property from the RC database, preventing property from conversion | Yes |  | 10-100 | High | No | Medium | Yes | Yes | Medium | 184 | Backlog | International | Conversions | Dan Davis
6 | HOS-17019 | cA | Connection reset when printing All Night Audit Reports | Running Night audit report requires more time (problemed report needs to be ran seperately) | Yes |  | 100+ | Low | Yes | Low | No | No | Low | 120 | Submitted | Other | Daily Ops | Kevin Hou
7 | HOS-10697 | RC | Promo child rates are showing active when the parent rate is not active. | Promo child rates are showing active when the parent rate is not active. | Yes |  | 100+ | High | Yes | Low | No | No | Low | 134 | Backlog | Revenue Management | Promotion | Kelly Money
8 | HOS-17986 | RC | Rate Plan MLOS locked at corporate able to be managed through range edit | properties are able to set a Rate Plan Min. LOS for SAPR1A and SAPR1B. Min LOS should not be possible for SAPR1 or SAPR2 | No |  | 100+ | Medium | Yes | Low | No | No | Medium | 65 | Backlog | Revenue Management | Daily Ops | Kelly Money
9 | HOS-8837 | RC | Issues with promo rates trying to add or extend date range on a promo code | Blocks date changes to promos | Yes | N | 10-100 | Medium | Yes | Low | No | No | Low | 386 | Backlog | Revenue Management | Daily Ops | Anne Gregory
10 | HOS-10959 | RC | Step 4 - RC - BAR Conversion Step 4 taking error "Property conversion to new Rates Center is in progress |  | No | N | 100+ | Low | No | Low | Yes | No | Medium | 311 | Backlog | Other | Conversions | Becky Snediker
11 | HOS-13805 | RC | RC Conversion Failure due to deadlock (this was found when ST and CHI monitored recent Extended Stay Conversions | Step 4 Failed on conversion, cause hotel to be down for reservation longer than necessary | No | N | 10-100 | Medium | No | Low | Yes | No | Medium | 205 | Submitted | Other | Conversions
12 | HOS-8041 | cA | Group Reservation with Non-Room Package cannot share charges with multiple guests | Cannot use automatic charge sharing | Yes | N | 100+ | Low | Yes | Medium | No | No | Low | 414 | Backlog | Revenue Management | Daily Ops | Kevin Hou
13 | HOS-18046 | RC | RC supports max preDOA, but cA does not support that functionality | User from cA are still able to book package that are set restraction for Max booking date from RC | No |  | 100+ | Medium | Yes | Low | No | No | Medium | 17 | Backlog | Revenue Management | Packages | Kelly Money
14 | HOS-1432 | cA | Reg Card is Not Displaying Guest Phone Number (AU) | Reg Card is Not Displaying Guest Phone Number (AU) | No |  | 10-100 | Low | No | High | No | No | Low | 729 | Backlog | International | Daily Ops | Anthony Stanley
15 | HOS-13237 | RC | Logs showing which user changed what are recording the wrong username at times due to issues with session management | At times, wholly different users from other properties appear to be making changes (but aren't) | No | N | 100+ | Low | Yes | Low | No | No | Medium | 228 | Backlog | Revenue Management | Daily Ops | Eddie Jaidi
16 | HOS-11346 | RC | Calendar in Rates Center under French Locale displays as Monday-Sunday (cusmetic) |  | No |  | 10-100 | Low | No | Low | No | No | Low | 305 | Backlog | International | Daily Ops | David Beers
17 | HOS-17330 | cA | Direct Bill Account overriding the Company Profile displayed on the Folio | For, guests check in with the with Company Profile A but needs to be billed to Direct Bill Account B, the guest folio generated during check out does not correctly reflect guest stay information. | Yes |  | 100+ | Low | Yes | Medium | No | No | Low | 129 | Backlog | Other | Daily Ops | Kevin Hou
98 | HOS-2395 | cA | SRD reimbursement amount is not being calculated correctly | Choice not reimburse correct amount for SRD stay at a property | Yes | N | 100+ | High | Yes | Low | No | No | Low | 610 | Backlog | International
99 | HOS-8665 | RC | When a property changes a parent APR (SAPR1/SAPR2) the shopping category "Prepaid" can be wiped, preventing the rate plan from being sold | Causes parity issues, root cause unknown | Yes | N | 100+ | Medium | Yes | Low | No | No | Low | 401 | Backlog | Revenue Management | Rate Parity | Adaora Isichei
| HOS-12973 | cA | cA - Crosssite scripting flaw at /InputReservation.do | Security Defect | No | N | [7 empty] | 413 |  | Security | Security | Scott Solomon
| HOS-9199 | cA | ST/cA - Manual CC Postings are not sending CustomerName to Shift4 | When a property posts a credit card payment and enters the information manually the CustomerName is not being included in the information sent to Shift4. The payment is still processed and accepted, but when settling the batch, or searching Shift4, the information is missing. The Name field is a required field. | No | N | 100+ | Low | Yes | Low | Yes | No | High | 365 | On-Hold | Other | Daily Ops
| HOS-15425 | cA | The monthly Cambria/Comfort Suites elite recognition file is missing member numbers | Unable to award points for the member without the member number | No | N | 100+ | Low | Yes | High | Yes | No | Critical | 155 | On-Hold | Choice Privilege | Daily Ops | Becky Snediker
| HOS-17317 | cA | When a group is changed from tentative to definite, a CREATE message is sent to CRS. While on the same screen, you modify the group (change the arrival of the group).. a MODIFICATION message is not sent to the CRS | Change of the arraival date for group fail to be updated in CRS | No |  | 100+ | High | Yes | Medium | Yes | No | Critical | 63 | Backlog | Other | Daily Ops | Kevin Hou
| HOS-10922 | RC | New child rate plans made at corporate will propagrate immediately upon creation | Cannot create new child rate plans until ready to use | No | N | [7 empty] | 325 | Selected for Development | Revenue Management | Daily Ops | Adaora Isichei
| HOS-11610 | RC | SCPM rate plan, and other elective rate plans from the coporate shows the inactive when propagated to properties. | Activating mandatory rate plans requires added time | Yes | N | 100+ | High | Yes | Low | No | No | Low | 295 | Backlog | Revenue Management | Daily Ops | Adaora Isichei
| HOS-12665 | RC | Promotion child rateplans getting inactivated when activating parent rateplan due to retail promo code being inactive | Inactiviating the child promo rate plan prevents sales from the OTA for promotion plan | Yes |  | 100+ | High | Yes | Medium | No | No | Low | 259 | Backlog | Revenue Management | Daily Ops | Sam Abazly
| HOS-10512 | RC | Multiple Proeprties cannot make changes to LEXP Rate Bucket | Could cause parity issues (Adoara) | No | N | 100+ | Medium | Yes | Low | No | No | Medium | 374 | Backlog | Revenue Management | Rate Parity | Adaora Isichei
| HOS-8331 | RC | APR plans deactivated at property level cannot be reactivated | Activiting APR requires added time | Yes | N | 100+ | Medium | Yes | Medium | No | No | Low | 374 | Backlog | Revenue Management | Daily Ops | Adaora Isichei
| HOS-11258 | RC | Incorrect Color on RC BAR Calendar for SmartRates Saved Rates | Cosmetic, but causes property confusion as it contradicts training | No | N | [7 empty] | 317 | RC 5.11 | Revenue Management | Smart Rates | Kitti Tong
| HOS-15547 | cA | PAYMENT OBJECT NULL | [9 empty] | Very Low | #N/A | cA 8.7
| HOS-2513 | RC | Property changes not reflected on Change History Report | Property changes not reflected on Change History Report | [8 empty] | Very Low | 889 | Backlog | Revenue Management | Report | Becky Snediker
| HOS-17778 | RC | [10 empty] | Very Low | 59 | Backlog | Other | Daily Ops
| HOS-17769 |  | defact Related to HOS-16518 | [10 empty] | #N/A
| HOS-17694 |  | Related to HOS-16519 | [9 empty] | Very Low | #N/A
| HOS-17693 |  | Epics Related to HOS-16520 | [9 empty] | Very Low | #N/A
| HOS-17707 |  | Related to HOS-16521 | [9 empty] | Very Low | #N/A
| HOS-17770 |  | Related to HOS-16522 | [9 empty] | Very Low | #N/A
| HOS-2232 | RC | Local Selling Limit Bucket Data is Not Displayed on Rate Configuration Report | [9 empty] | Very Low | 889 | Backlog | Revenue Management | Report
| HOS-18066 | RC | Children plans for SAPR 1and 2 and SMRC and SMRC2 do not load | [9 empty] | Very Low | 45
Formulas:
Age (days) = TODAY() - VLOOKUP([ST Jira HOS#],'Age Data (Hidden)'!$A:$C,3,FALSE)
Note on P7: Kevin Hou: Targeted for cA 8.7
Note on F8: Kevin Hou: Turn off auto post
Note on F10: Sam Abazly: The only workaround is to not mark it as a promo rate plan OR do not choose a 0% off rate bucket
Note on P10: Kevin Hou: Targeted for cA 8.8
Note on F11: Kevin Hou: Manually move one item line at a time
Note on P11: Kevin Hou: Target for cA 8.8
Note on B13: Kevin Hou: Just need to track this to make sure this get delivered
Note on F16: Sam Abazly: Print desired reports regularly in advance of potential outages OR if due to internet/power outage on site, print from another location
Note on P16: Kevin Hou: Move to backlog pending Choice responses to SSRS migration reqeust
Note on F17: Sam Abazly: Print desired reports regularly in advance of potential outages OR if due to internet/power outage on site, print from another location
Note on P17: Kevin Hou: Move to backlog pending Choice responses to SSRS migration reqeust
Note on E18: Sam Abazly: Is this a showstopper? How are we doing conversions today?
Note on D19: Kevin Hou: Impacting MLOS
Note on E19: Sam Abazly: Thought to be related to 10302, and we want them to be worked together
Note on F22: Kevin Hou: Package end end date is cA cannot be changed
Note on P22: Kevin Hou: 8.9
Note on F23: Kevin Hou: move the rooms in question to other rooms and then move them back to the original room so that the system refreshes the status of the room, create security concern (Kevin needs to clearfy this), check out and undo the check out immediately.
Note on N23: Kevin Hou: Enven this is "low" priority, we still rank this high, as this defect has significant impact on guest satisfaction and daily operation
Note on P23: Kevin Hou: Targeted for cA 8.9
Note on P25: Kevin Hou: Working with EAS to replicate this
Note on F27: Kevin Hou: Find out the CP number from AI.
Note on N28: Kevin Hou: Used not as often as no.7
Note on F29: Kevin Hou: Uncheck the removed room type from the package within cA
Note on F31: Kevin Hou: disable the Allow Event Rates By Day feature
Note on F33: Kevin Hou: Bi-weekly report, ST update that flag
Note on F35: Kevin Hou: Manually download and email
Note on F36: Kevin Hou: make a rate plan with the same package code, and then associate it to the package
Note on D40: Kevin Hou: Tax Invoice AR Tax Invoice Credit Note Folio (Group and House) Pro Forma (Guest, Group and House) Registration Card
Note on F41: Kevin Hou: rate plans have had the correct Channels added to them
Note on N41: Kevin Hou: Used not often
Note on F42: Kevin Hou: Remove some of the reports from the Night Audit batch. AR Aging is a time consuming report
Note on B43: Kevin Hou: Causing rate parity
Note on F43: Kevin Hou: activate the parent, then deactivate the parent to remove the child rates
Note on F45: Kevin Hou: Rebuild promo
Note on N46: Kevin Hou: Used not often
Note on N47: Kevin Hou: Used not often
Note on F48: Kevin Hou: Manually adjust folio
Note on B49: Kevin Hou: Might be a enhancement
Note on N51: Kevin Hou: Used not often
Note on F53: Kevin Hou: Possible solution is to change the company information on the guest info to match the direct bill account, print the folio so that it displays the correct information, and then change the guest info back to the original company profile
Note on F55: Sam Abazly: ST manually reports on this and fixes values daily
Note on E57: Sam Abazly: Will a property get charged back on this?
Note on P58: Kevin Hou: Dev requested more info on recreation steps.
Note on B61: Kevin Hou: 7
Note on C61: Kevin Hou: need to test if that impact CUG child
Note on F61: Kevin Hou: go to each property manually and click activate on the rate plan.
Note on A62: Kevin Hou: More commonly used feature, could cause parity issue
Note on B62: Kevin Hou: 9
Note on F62: Kevin Hou: Reactiviate the promo parent/child rate plan
Note on B63: Kevin Hou: 10
Note on D63: Sam Abazly: Need details on what causes this/how widespread this is
Note on B64: Kevin Hou: 11
Note on F64: Kevin Hou: delete from prop -> wait 3 days -> assign from corp
Note on A65: Kevin Hou: Top 10
Note on B67: Kevin Hou: Related to HOS-14978

## Legend
Attributes | Details
Weighting Factors
Work around? | Does the defect has a workaround ?
Number of properties | Number of property this defect could potentially impact
GRR Impact | Estimated impact towards the Gross Room Revenue (GRR)
Upscale Impact | Does the defect impact domastic upscale property?
Guest Satisfaction Impact | Estimated impact towards the guest satisfaction (guest-facing function)
Program Dependency | Defect the prevents function of other program (e.g SmartRate)
Repeating Problem | Was the defect fixed before and came back again?
Status
Blacklog | Defect has been recognized by SkyTouch, but has not been picked up by development
Submitted | Same as "Backlog", this is newly created defect that needs to be verified by QA
Under Review | Defect is being reviewed due to not been enough information provided when it was initially sent to development
Selected for Development | Very early stage in the development phase, defect will soon be worked on by development team
In Dev | Defect is being worked on by development team (from grooming to coding)
Release Planning | Coding is complete and within a release version, but it is still pending QA certification
QA Rejected | QA cannot recreate the defect or needing more information from Production Support team in SkyTouch

## Delivered Defects (hidden)
HOS# | Date Opened | Case/SR | Closed? | Delivered in | Delivered/Closed Date
HOS-10603 | 2016-03-29 |  | Delivered | RC 5.7.3 | 2016-07-28
HOS-9263 | 2016-03-09 |  | Delivered | RC 5.7.3 | 2016-07-28
HOS-575 | 2015-11-10 |  | Delivered | RC 5.9 | 2016-11-10
HOS-4766 | 2016-03-31 |  | Delivered | RC 5.9 | 2016-11-10
HOS-6130 | 2015-10-15 |  | Delivered | RC 5.9 | 2016-11-10
HOS-9900 | 2016-03-14 |  | Delivered | RC 5.13 | 2017-02-02
HOS-9633 | 2015-10-01 |  | Delivered | RC 5.13 | 2017-02-02
HOS-11129 | 2016-04-18 |  | Delivered | RC 5.7.3 | 2016-07-28
HOS-11256 | 2016-04-20 |  | Delivered | RC 5.9 | 2016-11-10
HOS-11429 | 2016-04-21 |  | Delivered | cA 8.5 | 2016-10-27
HOS-11435 | 2016-04-22 |  | Delivered | RC 5.10 | 2016-11-28
HOS-8755 | 2016-03-18 |  | Delivered | cA 8.5 | 2016-10-27
HOS-11381 | 2016-04-18 |  | Delivered | cA 8.2.0.14 | 2016-08-25
HOS-9679 | 2016-03-10 |  | Delivered | RC 5.9 | 2016-11-10
HOS-8749 | 2016-05-10 |  | Delivered | cA 8.2 | 2016-07-20
HOS-2428 | 2014-09-19 |  | Delivered | cA 8.5 | 2016-10-27
HOS-12627 | 2016-05-31 |  | Delivered | RC 5.7.3 | 2016-07-28
HOS-12500 | 2016-05-25 |  | Delivered | RC 5.7.3 | 2016-07-28
HOS-15890 | 2016-09-09 | 36908 | Delivered | RC 5.11 | 2016-12-15
HOS-10695 |  |  | Delivered | CH.COM fix on Oct.11 | 2016-10-11
HOS-14491 |  |  | Delivered | CR20666 and CR20867 | 2016-09-15

## Prioritization Calculations (hidden)
ST Jira HOS# | Work around? | Number of property | GRR Impact | Upscale Impact | Guest Satisfaction Impact | Program Dependency | Repeating Problem | Total | CHI Rank
HOS-10525 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Very Low
HOS-11599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
HOS-7973 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Very Low
HOS-13110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
HOS-8744 | 0 | 4 | 1 | 2 | 1 | 0 | 0 | 8 | Low
HOS-11254 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Very Low
HOS-16098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
HOS-5835 | 4 | 4 | 1 | 2 | 3 | 0 | 0 | 14 | High
HOS-11774 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Very Low
HOS-11440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
HOS-11952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
HOS-11023 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Very Low
HOS-14978 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Very Low
HOS-2281 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Very Low
HOS-16518 | 4 | 4 | 3 | 2 | 2 | 2 | 0 | 17 | Critical
HOS-2038 | 4 | 4 | 2 | 2 | 3 | 0 | 0 | 15 | High
HOS-14118 | 0 | 4 | 1 | 2 | 3 | 0 | 0 | 10 | Low
HOS-2322 | 4 | 4 | 1 | 2 | 3 | 0 | 0 | 14 | High
HOS-13227 | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 14 | High
HOS-657 | 4 | 4 | 1 | 2 | 2 | 0 | 0 | 13 | Medium
HOS-16405 | 0 | 4 | 1 | 2 | 3 | 0 | 0 | 10 | Low
HOS-14677 | 4 | 4 | 1 | 0 | 3 | 0 | 0 | 12 | Medium
HOS-1988 | 0 | 4 | 2 | 2 | 1 | 0 | 0 | 9 | Low
HOS-2317 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Very Low
HOS-17252 | 4 | 4 | 2 | 2 | 1 | 2 | 0 | 15 | High
HOS-17271 | 4 | 4 | 1 | 0 | 3 | 0 | 0 | 12 | Medium
HOS-15934 | 0 | 4 | 2 | 2 | 2 | 0 | 2 | 12 | Medium
HOS-1398 | 4 | 3 | 1 | 0 | 3 | 0 | 0 | 11 | Low
HOS-2445 | 0 | 4 | 1 | 2 | 3 | 0 | 0 | 10 | Low
HOS-17287 | 0 | 4 | 2 | 2 | 3 | 0 | 0 | 11 | Low
HOS-10579 | 4 | 4 | 3 | 2 | 1 | 2 | 0 | 16 | Critical
HOS-17331 | 4 | 3 | 3 | 2 | 1 | 0 | 0 | 13 | Medium
HOS-17692 | 4 | 4 | 1 | 2 | 1 | 0 | 0 | 12 | Medium
HOS-14662 | 4 | 4 | 1 | 0 | 3 | 0 | 0 | 12 | Medium
HOS-16469 | 0 | 3 | 3 | 0 | 2 | 2 | 2 | 12 | Medium
HOS-17019 | 0 | 4 | 1 | 2 | 1 | 0 | 0 | 8 | Low
HOS-10697 | 0 | 4 | 3 | 2 | 1 | 0 | 0 | 10 | Low
HOS-17986 | 4 | 4 | 2 | 2 | 1 | 0 | 0 | 13 | Medium
HOS-8837 | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 8 | Low
HOS-10959 | 4 | 4 | 1 | 0 | 1 | 2 | 0 | 12 | Medium
HOS-13805 | 4 | 3 | 2 | 0 | 1 | 2 | 0 | 12 | Medium
HOS-8041 | 0 | 4 | 1 | 2 | 2 | 0 | 0 | 9 | Low
HOS-18046 | 4 | 4 | 2 | 2 | 1 | 0 | 0 | 13 | Medium
HOS-1432 | 4 | 3 | 1 | 0 | 3 | 0 | 0 | 11 | Low
HOS-13237 | 4 | 4 | 1 | 2 | 1 | 0 | 0 | 12 | Medium
HOS-11346 | 4 | 3 | 1 | 0 | 1 | 0 | 0 | 9 | Low
HOS-17330 | 0 | 4 | 1 | 2 | 2 | 0 | 0 | 9 | Low
HOS-2395 | 0 | 4 | 3 | 2 | 1 | 0 | 0 | 10 | Low
HOS-8665 | 0 | 4 | 2 | 2 | 1 | 0 | 0 | 9 | Low
HOS-12973 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Very Low
HOS-9199 | 4 | 4 | 1 | 2 | 1 | 2 | 0 | 14 | High
HOS-15425 | 4 | 4 | 1 | 2 | 3 | 2 | 0 | 16 | Critical
HOS-17317 | 4 | 4 | 3 | 2 | 2 | 2 | 0 | 17 | Critical
HOS-10922 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Very Low
HOS-11610 | 0 | 4 | 3 | 2 | 1 | 0 | 0 | 10 | Low
HOS-12665 | 0 | 4 | 3 | 2 | 2 | 0 | 0 | 11 | Low
HOS-10512 | 4 | 4 | 2 | 2 | 1 | 0 | 0 | 13 | Medium
HOS-8331 | 0 | 4 | 2 | 2 | 2 | 0 | 0 | 10 | Low
HOS-11258 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | Very Low
HOS-15547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
HOS-2513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
HOS-17778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
HOS-17769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
HOS-17694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
HOS-17693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
HOS-17707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
HOS-17770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
HOS-2232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
HOS-18066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very Low

## Prioritization Scoring Weights (hidden)
| Weight | Value |  |  | Score
Work around | 20% | 20 |  | HOS-10579 | 4
No | 20% | 4
Yes | 0% | 0
Number of properties | 20% | 20 |  |  | 4
100+ | 20% | 4
10-100 | 15% | 3
Less than 10 | 10% | 2
GRR Impact | 15% | 20 |  |  | 3
High | 15% | 3
Medium | 10% | 2
Low | 5% | 1
Upscale Impact | 10% | 20 |  |  | 2
Yes | 10% | 2
No | 0%
Guest Satisfaction Impact | 15% | 20 |  |  | 1
High | 15% | 3
Medium | 10% | 2
Low | 5% | 1
Program Dependency | 10% | 20 |  |  | 2
Yes | 10% | 2
No
Repeating Problem | 10% | 20 |  |  | 0
Yes | 10% | 2
No | 0%
Total Prioritization Point | 100%
Prioritization Levels |  |  | Total Points |  | 16
Value
| 0 | Very Low
| 7.5 | Low | 19 | 44.19%
| 12 | Medium | 14 | 32.56%
| 14 | High | 6 | 13.95%
| 16 | Critical | 4 | 9.302%